## Slide 1: Investigation of Vulnerabilities in Open RAN Implementations
Research Project – WS 22/23
Arnova Abdullah
Weekly meeting-09 (15.12.2022)

## Slide 2
Previous Weeks Meeting Details
Week 1 Meeting (19.10.2022)
  Basics about Radio Access Network (History, parts of RAN for 1G, 2G, 3G, 4G)
  Basics about Open RAN (Distribution unit, central unit, user plane, control plane, interfaces, front haul, mid haul, backhaul)
  Open RAN risk analysis (Stakeholders of attackers-User, external attacker, cloud operator**, RAN operator**)
Week 2 Meeting (26.10.2022)
  Installation of Kali Linux and Metasploitable
  Atomic Red Team GitHub repository download
  Research other open-source attack tools
Week 3 Meeting (02.11.2022)
  Penetration testing using Kali Linux
  Try Atomic tests by invoke-atomic
  Get used to commands used for running a test
  Research details about one of the attack tools - Infection Monkey
  Read research papers on the risk of 5G open RAN
Week 4 Meeting (09.11.2022)
  Finding the most relatable attacks from the MITRE ATTACK list (On going)
  CyberOps course ongoing
  Research paper by MOU

## Slide 3
Previous Weeks Meeting Details
Week 5 Meeting (17.11.2022)
  Install Infection monkey (Need AWS subscription, don’t continue anymore!!)
  Start learning Docker container
    https://developer.cisco.com/learning/tracks/containers/
    https://learning.oreilly.com/videos/docker-fundamentals-for/9781803237428/9781803237428-video1_1/
Week 8 Meeting (08.12.2022)
Make a comparison between Kali Linux tools and Atomic Red Team
  Select one to use at the end of the project

## Slide 4
Week 9 (Until 15.12.2022)
Create a list for Docker, and Kubernetes attack:
  How to attack the docker container?
  What are the tools? (If required any)
  What are the known vulnerabilities? (CVE, MITRE)
Create a list for Ubuntu:
  How to attack Ubuntu?
  What are the tools? (If required any)
  What are the known vulnerabilities? (CVE, MITRE)
Try to install Atomic red team in Kali Linux

## Slide 5
Research
CVE List:
  https://www.cvedetails.com/vulnerability-list/vendor_id-4781/product_id-20550/opginf-1/Canonical-Ubuntu-Linux.html
  https://cve.mitre.org/find/search_tips.html
  I didn’t find anything for open RAN. But there are some rules for searching with keywords. I will research and find this.

## Slide 6
Next Steps (Week 10)
Create a list for Docker, and Kubernetes attack:
  How to attack the docker container?
  What are the tools? (If required any)
  What are the known vulnerabilities? (CVE, MITRE)
Create a list for Ubuntu:
  How to attack Ubuntu?
  What are the tools? (If required any)
  What are the known vulnerabilities? (CVE, MITRE)
Try to install Atomic red team in Kali Linux