## Slide 1
Research Project WS 22/23
Arnova Abdullah
Weekly Meeting – 25.01.2023

## Slide 2
Previous Weeks Meeting Details
Week 1 Meeting (19.10.2022)
  Basics about Radio Access Network (History, parts of RAN for 1G, 2G, 3G, 4G)
  Basics about Open RAN (Distribution unit, central unit, user plane, control plane, interfaces, front haul, mid haul, backhaul)
  Open RAN risk analysis (Stakeholders of attackers-User, external attacker, cloud operator**, RAN operator**)
Week 2 Meeting (26.10.2022)
  Installation of Kali Linux and Metasploitable
  Atomic Red Team GitHub repository download
  Research other open-source attack tools
Week 3 Meeting (02.11.2022)
  Penetration testing using Kali Linux
  Try Atomic tests by invoke-atomic
  Get used to commands used for running a test
  Research details about one of the attack tools - Infection Monkey
  Read research papers on the risk of 5G open RAN
Week 4 Meeting (09.11.2022)
  Finding the most relatable attacks from the MITRE ATTACK list (On going)
  CyberOps course ongoing
  Research paper by MOU

## Slide 3
Previous Weeks Meeting Details
Week 5 Meeting (17.11.2022)
  Install Infection monkey (Need AWS subscription, don’t continue anymore!!)
  Start learning Docker container
    https://developer.cisco.com/learning/tracks/containers/
    https://learning.oreilly.com/videos/docker-fundamentals-for/9781803237428/9781803237428-video1_1/
Week 8 Meeting (08.12.2022)
Make a comparison between Kali Linux tools and Atomic Red Team
  Select one to use at the end of the project
Week 9 Meeting (15.12.2022)
No update

## Slide 4
Previous Weeks Meeting Details
Week 10 Meeting (21.12.2022)
  Research:
    Is there a map between MITRE ID to CVE list?
    In Kali Linux, is there any tool or settings to map CVE or MITRE ID?
    Create an extended comparison between Atomic and Kali in MS Excel (Not done yet)
  Create a list for Docker, and Kubernetes attacks:
    How to attack the docker container? Which version?
    What are the tools? (If required any)
    What are the known vulnerabilities? (CVE, MITRE)
  Create a list for Ubuntu:
    Which Ubuntu version?
    How to attack Ubuntu?
    What are the tools? (If required any)
    What are the known vulnerabilities? (CVE, MITRE)
Week 11 Meeting (11.01.2023)
Research more about Vulmap.
  Which type of attack can it do?
  Install it in Kali Linux and have practical experience with it.
Do the lab of Docker from Devnet.
  If it is installed, then try some attacks with kali and atomic by mapping to CVE/MITRE. Use the list from the previous page list. (Partially done!)

## Slide 5
Week 13 Meeting (25.01.2023)
Problem with understanding the attack result of the Operating System. So, no special update this week!

## Slide 6
Meeting Discussion
Don’t use DevNet VM, instead create another VM with Ubuntu 20.04.
Need to learn Kubernetes and its process because now need to focus on the containerized application instead of OS.
  Dive deep into Kubernetes (Install your own Kubernetes environment)
  Try to find vulnerabilities in Kubernetes (See CVE list)
  For mapping CVE to MITRE, need to learn every detail of the configuration of Kubernetes so that the attack (outside or inside) result can be analyzed properly.

## Slide 7
Next Step -- 01.02.2023 (13:00)
1. Create another VM with Ubuntu 20.04
2. Install Kubernetes in the newly installed VM
Documentation link: https://kubernetes.io/
2 (a) Learn the basics of architecture
2 (b) Learn the meaning of the important keywords (namespaces, clusters, object, etc)